## Test Case Format
Sr.No | Scenario Id | Scenario objective | Test Case Id | Test case Objective | Steps | Test Data | Expected Result | Actual Result | Status | Tester Name | Remark
1 | sc_01 | To verify Login functionality | tc_001 | To verify user is able to login with correct credentials | 1 Enter Email 2 Enter Password 3 click on login btn | Email-gitakadam@gmail.com Password-56789 | login should be successful | login successful | Done | Gitanjali | apply sweet alerts
2 |  |  | tc_002 | To verify user is able to login with username ,incorrect password | 1 Enter Email 2 Enter Wrong Password 3 click on login btn | Email-gitakadam@gmail.com Password-567890 | user should not be able to login user should get pop up "Wrong password" | incorrect password | Done | Sanika | _
3 | sc_02 | To verify Register functionality | tc_003 | To verify user is able to login with correct credentials | 1 Enter Fullname- 2 Enter Mobile number 3 Enter Email 4 Enter Designation 5 Enter Department 6 Enter Password 7 Enter Employee ID 8 Enter Confirm Password | Fullname- Aditi Muley Mobile No.-1234567890 Email-aditi123@gmail.com Designation-25 Department-Computer Password-Aditi@123 Employeee ID-7890 Confirm Password-Aditi@123 | Registration Should be successful | Registration Successful | Done | Tanishka | Register Successful heading should be large
|  |  | tc_004 | To verify user is able to login with correct credentials | 1 Enter Fullname- 2 Enter Mobile number 3 Enter Email 4 Enter Designation 5 Enter Department 6 Enter Password 7 Enter Employee ID 8 Enter Confirm Password | Fullname-Aditi Muley Mobile No.1234567890 Email-adit123@gmail.com Designation-25 Department-Computer Password-aditi@123 Employee ID-7890 Confirm Password-aditi@123 | user should not be able to register user get pop up with wrong password | incorrect password | Done | Aditi | _

## Bug Report
Sc_ID | TC_ID | User Type | Bug Id | Bug Description | Feature Name | Page Name | Priority | Allocated To | Developer Status | Tester Status | Tester Name | Remark
sc_01 | tc_001 | User | bug_01 | On the first page, when we click on the top bar option (e.g., Total Books), it does not navigate correctly to the Total Books panel." | Login | login.php | P3 |  |  | Fail | Gitanjali | Top bar navigation for the Total Books option is not working correctly; the respective panel does not open after clicking."
sc_02 | tc_003 | user | bug_02 | "On the registration page, any user who registers can become an admin after logging in." | Registration | registor.php | P2 |  |  | Fail | Tanishka | "Normal users are getting admin access after registration and login."
sc_03 | tc_002 | user | bug_03 | "On the registration page, the restriction for the ID (minimum/maximum four characters or digits) was not displayed on the registration form itself. It was shown only after clicking on the registration button and moving to the next page." | Login | login.php | P1 |  |  | Fail | Sanika | ID length restriction is missing on the registration form and is shown later."
sc_04 | tc_004 | user | bug_04 | "After registration, the 'Registered Successfully' message is not displayed prominently. It should be shown in a larger and more visible format." | Registration | register.php | P3 |  |  | Fail | Aditi | "Success message is too small and not clearly visible after registration."
sc_05 | tc_005 | user | bug_05 | The website shows 2500+ student registrations, but the registered students are not displayed. | Login | login.php | p1 |  |  | fail | Gitanjali | "Registered student count is displayed, but student details are not showing."